## Simple Gantt Chart - EX
TOPIC | ROLE-BASED SELF-SOVEREIGN IDENTITY FOR ASSET MANAGEMENT IN A WAREHOUSE
PROFESSOR | Prof. Uwe Aßmann
SUPERVISOR | Orçun Oruç
DATE | 2022-07-12
THESIS PLANNING
| TASK | START | DUE | DURATION | TASK | [10 empty] | WEEKS
| TITLE | DATE | DATE | IN DAYS | COMPLETE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
| Understanding the technology | 2022-08-15 | 2022-09-04 | 20 | 0%
| Reading | 2022-08-15 | 2022-09-04 | 20 | 0%
| Review and research | 2022-08-22 | 2022-09-11 | 20 | 0%
| Implementation | 2022-09-05 | 2022-12-04 | 90 | 0%
| Testing and Evaluation | 2022-10-03 | 2022-12-04 | 62 | 0%
| Writing | 2022-11-07 | 2023-01-08 | 62 | 0%
| Presentation | 2023-01-09 | 2023-01-22 | 13 | 0%

## Simple Gantt Chart - BLANK
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter |  |  |  |  | 100%
1.1.1 | Project Charter Revisions |  |  |  |  | 0%
1.2 | Research |  |  |  |  | 0%
1.3 | Projections |  |  |  |  | 0%
1.4 | Stakeholders |  |  |  |  | 0%
1.5 | Guidelines |  |  |  |  | 0%
1.6 | Project Initiation |  |  |  |  | 0%
2 | Project Definition and Planning
2.1 | Scope & Goal Setting |  |  |  |  | 0%
2.2 | Budget |  |  |  |  | 0%
2.3 | Communication Plan |  |  |  |  | 0%
2.4 | Risk Management |  |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status & Tracking |  |  |  |  | 0%
3.2 | KPIs |  |  |  |  | 0%
3.2.1 | Monitoring |  |  |  |  | 0%
3.2.2 | Forecasts |  |  |  |  | 0%
3.3 | Project Updates |  |  |  |  | 0%
3.3.1 | Chart Updates |  |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  |  |  |  | 0%
4.2 | Quality Deliverables |  |  |  |  | 0%
4.3 | Effort and Cost Tracking |  |  |  |  | 0%
4.4 | Project Performance |  |  |  |  | 0%