## Simple Gantt Chart - EX
TOPIC | SMART CONTRACT DEVELOPMENT WITH JASON BDI AGENTS
PROFESSOR | Prof. Uwe Aßmann
SUPERVISOR | Orçun Oruç
START DATE | 2022-08-15
SUBMISSION | 2023-01-23
THESIS PLANNING
| TASK | START | DUE | DURATION | TASK | [10 empty] | WEEKS
| TITLE | DATE | DATE | IN DAYS | COMPLETE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
| Understanding the technology | 2022-08-15 | 2022-09-04 | 20 | 0%
| Reading | 2022-08-15 | 2022-09-04 | 20 | 0%
| Review and research | 2022-08-22 | 2022-09-11 | 20 | 0%
| Implementation | 2022-09-05 | 2022-12-04 | 90 | 0%
| Testing and Evaluation | 2022-10-03 | 2022-12-04 | 62 | 0%
| Writing | 2022-11-07 | 2023-01-08 | 62 | 0%
| Presentation | 2023-01-09 | 2023-01-22 | 13 | 0%